## 19-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | No | Yes | 8.45 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10.15 | 6.2 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | No | Yes | 9.45 | 5.45 | Understanding Use Cases_Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Understanding Document of Interoptebilty and Interim review of theoretical prices
5 | Kritika Manek | Yes | No | 9.5 | 5.45 | Test Scenario and Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9.5 | 5.3 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request for CM Segment
9 | Nitesh Bedi | Yes | No | 9:50 | 6:30 | Understanding the "Settlement Module FD" for meeting scheduled for tomorrow; Working on scenarios for Performance Testing
10 | Pratiksha Talekar | Yes | No | 9:30 | 6 | Test case preparation forAPI Testing - Collateral flow; discussed "Modified Trade" flow with Nitesh
11 | Pruthviraj Jadhav | Leave | No | NA | NA
12 | Gautami Karkal | Leave | No | NA | NA

## 20-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 11 | 4 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10 | 4 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | Yes | No | 9.45 | 5.45 | Mentoring of team, Settlement Webex Session and Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Settlement Webex Session, Team Discussion and Understanding Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Scenario and Test Cases writing for Clearing DPD and Settlement Webex Session
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit for CD and Debt
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request and Allocation for CM Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 5:30 | Reviewing performance testing scenarios; Understanding settlement flow
10 | Pratiksha Talekar | Yes | No | 9:30 | 5:30 | Test case preparation forAPI Testing - Collateral flow completed; Review pending with Nitesh
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 5:30 | Prepared test scenarios for performance testing; setting up automation tools
12 | Gautami Karkal | Yes | No | 10:15 | 5:15 | Started with CI/CD tools integration with TOSCA and Selenium

## 23-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9.3 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9.45 | 6 | Test Cases on Theoretical Pricing and restructuring of formula
3 | Mohnish Motwani | Yes | No | 9.45 | 6 | Understanding use case of settlement and Physical Settlement document
4 | Amardas Gangula | Yes | No | 9.45 | 6 | TC Review of Therotical Pricing and document understanding of Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Cases writing for Clearing DPD Theoretical price review
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI Allocation, Securties EPI (CM &SLB)
9 | Nitesh Bedi | Yes | No | 9:30 | 6:30 | Discussion on performance testing scenarios; Understanding settlement flow; Reviewing "API Collateral Test cases"
10 | Pratiksha Talekar | Yes | No | 9:30 | 6:00 | Test case preparation forAPI Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 6:30 | Prepared test scenarios for performance testing; Initiated discussion with Ami/Laxman; set up automation tools
12 | Gautami Karkal | Yes | No | 10:00 | 5:45 | Created new project with Selenium; Set up Jenkins

## 24-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test case preparation for Pricing DPD and Clearing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement and review of Pricing Test cases
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposits for CM segments
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Reviewing "API Collateral Test cases"; scheduled meeting with mentee's on performance testing approach; set up of git and ci/cd in progress
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Initiated discussion and prepared questionaire for discussion with mentees; set up automation tools; started with automation script
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | setup of jenkins and selenium project; command line execution of executable using Jenkins
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 25-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test cases preparation of Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement.
4 | Amardas Gangula | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement,TC Review of Therotical Pricing
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposit for FO segment
9 | Nitesh Bedi | Yes | No | 9:00 | 17:30 | Review and discuss "API Collateral Test cases"; Discusssion on PT - open questions
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Discussion with mentees on PT open questions; set up automation tools - selenium and GIT
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Jenkins plugins for selenium;Login script for orange hrms ready
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 26-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Cases on Pricing DPD and Theoretical Pricing Review
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Reviewed point discussed of Theoretical Pricing, Understanding Physical Settlement Document
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases on Clearing DPD and Theoretical Pricing Review
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Going through SLA Document for PT; setup of Git; Review of API Collateral test cases
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document;set up automation tools - selenium; Sample script created
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Login script for orange hrms ready; automated execution using Jenkins in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 27-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:10 | Test Cases on Pricing DPD, Discussion and Review of Throretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Reviewed point discussed of Theoretical Pricing and reviewed test cases of Clearing DPD
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Creation of Document for JIRA
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release File Upload
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Review of API Collateral test cases; Understanding SLA document for PT; Going through settlement FD
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Unchecked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document; Shared questions to be discussed on Monday with Mentees
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | automated execution using Jenkins-currently facing issues; Understanding the Settlement Orchestrator FD
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 30-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:00 | Test cases on Pricing DPD and Theoretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Reviewed point of SO FD discussed with team and discussed/resolved queries of Use case collateral.
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Reviewed point of Theoretical Pricing discussed with team and queries discussed with Mentees.
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases in Clearing Use Cases and Theoretical Pricing
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases on Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release CM Segment
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release CD Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /Unchecked scenario)-Settled
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 31-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar
2 | Mohammed Shadab
3 | Mohnish Motwani
4 | Amardas Gangula
5 | Kritika Manek
6 | Kabir Gor
7 | Sana K
8 | Forum Rathod
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /checked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 1-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar
2 | Mohammed Shadab
3 | Mohnish Motwani
4 | Amardas Gangula
5 | Kritika Manek
6 | Kabir Gor
7 | Sana K
8 | Forum Rathod
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00
12 | Gautami Karkal | Yes | No | 10:00 | 18:00
13 | Anita Shinde | Yes | No | 10:00 | 18:30

## 3-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar
2 | Mohammed Shadab
3 | Mohnish Motwani
4 | Amardas Gangula
5 | Kritika Manek
6 | Kabir Gor
7 | Sana K
8 | Forum Rathod
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00
12 | Gautami Karkal | Yes | No | 10:00 | 18:00
13 | Anita Shinde | Yes | No | 10:00 | 18:30