## 19-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | No | Yes | 8.45 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10.15 | 6.2 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | No | Yes | 9.45 | 5.45 | Understanding Use Cases_Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Understanding Document of Interoptebilty and Interim review of theoretical prices
5 | Kritika Manek | Yes | No | 9.5 | 5.45 | Test Scenario and Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9.5 | 5.3 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request for CM Segment
9 | Nitesh Bedi | Yes | No | 9:50 | 6:30 | Understanding the "Settlement Module FD" for meeting scheduled for tomorrow; Working on scenarios for Performance Testing
10 | Pratiksha Talekar | Yes | No | 9:30 | 6 | Test case preparation forAPI Testing - Collateral flow; discussed "Modified Trade" flow with Nitesh
11 | Pruthviraj Jadhav | Leave | No | NA | NA
12 | Gautami Karkal | Leave | No | NA | NA

## 20-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 11 | 4 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10 | 4 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | Yes | No | 9.45 | 5.45 | Mentoring of team, Settlement Webex Session and Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Settlement Webex Session, Team Discussion and Understanding Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Scenario and Test Cases writing for Clearing DPD and Settlement Webex Session
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit for CD and Debt
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request and Allocation for CM Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 5:30 | Reviewing performance testing scenarios; Understanding settlement flow
10 | Pratiksha Talekar | Yes | No | 9:30 | 5:30 | Test case preparation forAPI Testing - Collateral flow completed; Review pending with Nitesh
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 5:30 | Prepared test scenarios for performance testing; setting up automation tools
12 | Gautami Karkal | Yes | No | 10:15 | 5:15 | Started with CI/CD tools integration with TOSCA and Selenium

## 23-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9.3 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9.45 | 6 | Test Cases on Theoretical Pricing and restructuring of formula
3 | Mohnish Motwani | Yes | No | 9.45 | 6 | Understanding use case of settlement and Physical Settlement document
4 | Amardas Gangula | Yes | No | 9.45 | 6 | TC Review of Therotical Pricing and document understanding of Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Cases writing for Clearing DPD Theoretical price review
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI Allocation, Securties EPI (CM &SLB)
9 | Nitesh Bedi | Yes | No | 9:30 | 6:30 | Discussion on performance testing scenarios; Understanding settlement flow; Reviewing "API Collateral Test cases"
10 | Pratiksha Talekar | Yes | No | 9:30 | 6:00 | Test case preparation forAPI Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 6:30 | Prepared test scenarios for performance testing; Initiated discussion with Ami/Laxman; set up automation tools
12 | Gautami Karkal | Yes | No | 10:00 | 5:45 | Created new project with Selenium; Set up Jenkins

## 24-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test case preparation for Pricing DPD and Clearing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement and review of Pricing Test cases
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposits for CM segments
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Reviewing "API Collateral Test cases"; scheduled meeting with mentee's on performance testing approach; set up of git and ci/cd in progress
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Initiated discussion and prepared questionaire for discussion with mentees; set up automation tools; started with automation script
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | setup of jenkins and selenium project; command line execution of executable using Jenkins
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 25-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test cases preparation of Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement.
4 | Amardas Gangula | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement,TC Review of Therotical Pricing
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposit for FO segment
9 | Nitesh Bedi | Yes | No | 9:00 | 17:30 | Review and discuss "API Collateral Test cases"; Discusssion on PT - open questions
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Discussion with mentees on PT open questions; set up automation tools - selenium and GIT
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Jenkins plugins for selenium;Login script for orange hrms ready
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 26-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Cases on Pricing DPD and Theoretical Pricing Review
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Reviewed point discussed of Theoretical Pricing, Understanding Physical Settlement Document
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases on Clearing DPD and Theoretical Pricing Review
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Going through SLA Document for PT; setup of Git; Review of API Collateral test cases
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document;set up automation tools - selenium; Sample script created
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Login script for orange hrms ready; automated execution using Jenkins in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 27-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:10 | Test Cases on Pricing DPD, Discussion and Review of Throretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Reviewed point discussed of Theoretical Pricing and reviewed test cases of Clearing DPD
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Creation of Document for JIRA
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release File Upload
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Review of API Collateral test cases; Understanding SLA document for PT; Going through settlement FD
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Unchecked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document; Shared questions to be discussed on Monday with Mentees
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | automated execution using Jenkins-currently facing issues; Understanding the Settlement Orchestrator FD
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 30-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:00 | Test cases on Pricing DPD and Theoretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Reviewed point of SO FD discussed with team and discussed/resolved queries of Use case collateral.
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Reviewed point of Theoretical Pricing discussed with team and queries discussed with Mentees.
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases in Clearing Use Cases and Theoretical Pricing
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases on Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release CM Segment
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release CD Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /Unchecked scenario)-Settled
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 31-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test cases on Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 19:00 | Review meeting(Client & Team),reviewed point of SO FD discussed with team and discussed/resolved queries of Use case collateral.
4 | Amardas Gangula | Yes | No | 9:45 | 19:00 | Review meeting(Client & Team),Reviewed point of Theoretical Pricing, Clearing DPD discussed with team and queries discussed with Mentees.
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Document Understanding of Clearing Use Cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases on Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release FO Segment
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release for Debt Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /checked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 01-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Understanding of Risk Use Cases
3 | Mohnish Motwani | Yes | No | 9:45 | 18:00 | Use case document understanding Settlement and query resolving Collateral
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Use case document understanding Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Understanding of Clearing Use Cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Understanding of Settlement Use Cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Review of Collateral Haircut Test Cases
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Understanding of Clearing Use Cases
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Discussion on Git setup with the team; Discussion on SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Created test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /checked and Unchecked/Unchecked - Settled; All scenarios for Deposit Cash:Margin Deposit completed
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Setup Of Git Bash and Git GUI ; Understanding Basic Git Commands ;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 03-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Haircut use cases review changes
2 | Mohammed Shadab | Yes | No | - | - | Leave
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Use case document understanding Settlement and query resolving Collateral with Deba
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Use case document understanding Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Clearing use case Test scenario design
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Document Understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Haircut use cases test case design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Clearing use case Test scenario design
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Understanding the SLA document; Planned discussion on the Settlement module
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Understanding Modified trade flow For following scenarios1.Trade Insert - for Cash Market2. Rectify Quantity
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding the SLA document; Setup of Cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 17:30 | Git Basic Understanding Complete ;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 07-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Understanding of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Going through the Interface Flow diagram; preparing points for meeting with mentees on PT SLA
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted-> Settled)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document and Interface service flow; working on cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Working on keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 08-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario review changes for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Scenario Creation of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Discussion on SLA document for PT with Mentees; Going through the Interface Flow diagram; Scheduled meetings to discuss on the Modified Trade and Settlement flow
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted->Manually Settled); Understanding Modified Trade Flow for Rectify Quantiy
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Discussion on SLA document for PT; Working on cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Working on keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 09-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario review changes for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Scenario Creation of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement session with non functional team
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Started with Test Execution plan for PT; Discussed review comments with Pruthvi on Trade flow test cases; Had internal team call for functional walk through of settlement module; Completed reverse KT/open questions with Niranjan on the Modified Trade Flow
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted->Manually Rejected)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Preparing ppt for PT ; Discussion on normal trade flow test cases; Discussion on rectified trade flow with nirajan; Dicussion on settlement module
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Completed with Keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 13-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use case test scenario design
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review of Test scenario for clearing use cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases design for settlement use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Test cases design for collateral use case
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review of Test scenario for clearing use cases
9 | Nitesh Bedi | Yes | No | 9:30 | 18:30 | Preparing PT Execution Plan; Reviewing trade flow test cases; Setting up Jenkins and Selenium
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-Checked-Margin Deposit Scenario(for Created->Accepted->Settled) Explained Modified Trade flow to Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding Modified Trade flow; Preparation of test cases for modified trade flow
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Read FD for Settlement Orchestrator and prepared Flow for the same;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 15-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use case documnet understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | PPT preparation of risk doc
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of settlement Withheld security
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of Clearing Offline Position Limit
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Review changes incorporation of Settlement use case doc
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use case documnet understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
9 | Nitesh Bedi | Yes | No | 9:30 | 18:30 | Preparation of the PT Test execution ppt; Understanding the Interface flow diagram
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-Checked-Margin Deposit Scenario(for 1. Created->Accepted->Manually Settled 2. Created->Accepted->Manually Rejected) Reviewed Normal Trade flow Test cases which is written by Pruthvi & after reviewing updated those test cases based on the flow.
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding Modified Trade flow; Prepared test scenarios for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Upload Java Code in git
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 16-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use cases test scenario designed
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases test scenario designed
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of Collateral Haircut
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of M2M
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SO CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use cases test scenario designed
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Working on "Test execution plan" for PT; reviewing trade flow test cases; Checking on application connection issues through VDI
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-UnChecked-Margin Deposit Scenario(for Created->Accepted-> Settled
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | setup for VDI ;Preparation of test cases for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Test flow diagram for SO and understanding SO message code
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 17-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use cases test scenario design
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases test scenario design
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of Collateral Haircut
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of M2M
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Theoritical pricing test case review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SO CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use cases test scenario design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Mapping of mindtree clearing test cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Preparing PT "Test execution" plan; reviewed SO flow scenarios; Checking on application access issue from remote desktop
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-UnChecked-Margin Deposit Scenario(for Created->Accepted-> Settled) 2. Disussed the queries regarding CB0 message with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 17:55 | Understanding CB0 fields validation on validator;Preparation of test cases for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Prepared test scenarios for SO
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 20-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing Use cases (Offline Position Limit) document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Review of Theoretical Prices Test Cases
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Theoritical pricing test case review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SSI CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing Use cases (Offline Position Limit) document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Mapping of mindtree clearing test cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Working on PPT and "Test execution plan" for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - Checked-Checked- Security Deposit Scenario (for a. Created->Accepted-> Settled b. Created->Accepted-> Manually Settled) 2. Discussed with Pruthvi on what Testcases should be included to cover CD284 broadcast message
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Prepared test cases for normal trade flow; Preparing test cases for rectified trade flow(1st 3 broadcast messages completed)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Tosca Installation and Setup ; Started with the orange hrms automation
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 21-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Cross functinal trainning
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SSI CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - Checked-Checked- Security Deposit Scenario (for a. Created->Accepted-> Manually Rejected) Collateral Deposit Cash - Unchecked-Checked- Security Deposit Scenario (for a. Created->Accepted->Settled)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Preparing test cases for rectified trade flow(5 broadcast messages completed)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Tosca cl client setup ready;Tosca with jenkins integration completed;result printing on jenkins pending;review from nitesh pending
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 22-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor/SSI cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Cross functional trainning
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - UnChecked-Checked- Security Deposit Scenario 2. Discussed with Pruthvi on modified trade flow tc
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Preparing test cases for rectified trade flow(6 broadcast messages completed);Discussed with pratiksha on one broadcast message
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Completed tosca result printing on jenkins; Rectified test flow and scenario after review from nitesh
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 23-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing use case document summary preparation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Cross functional trainning
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Incorporation of review points of Risk use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use case doc review test scenario design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Discussed Modified Trade Flow Test Cases with Pruthvi 2. Checked Security Deposit flow for Checked - Checked scenario in validator
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:55 | Updated test cases for rectified trade flow; Preparing test cases for rectified trade flow(7 broadcast messages completed);Discussed with pratiksha on one broadcast message
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Writing test cases for settlement orchestrator
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 24-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case doc understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Cross functional trainning and Risk review Session
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Incorporation of review points of Risk use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use case doc review test scenario design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - UnChecked-UnChecked- Security Deposit Scenario 2. Discussed modified trade flow tc with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:55 | Preparing test cases for rectified trade flow(8 broadcast messages completed);Discussed with pratiksha on one broadcast message
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Writing test cases for settlement orchestrator ob10003 complete
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 27-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case doc understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Leave
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Cross functional trainning and Test execution Plan Prepartation
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Incorporation of review points of Risk use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Settlement use case doc understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc walkthrough preparation
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Going through Interface Service Flow ppt 2. Discussed modified trade flow TC & explained CB10019 message to Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:55 | Preparing test cases for rectified trade flow;executing load combination for performance testing;going through the interface flow diagram
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Writing test cases for settlement orchestrator
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 28-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case Doc preparation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use case Doc preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Cross functional trainning and Test execution Plan Prepartation
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Incorporation of review points of Risk use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case Doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case Doc preparation
7 | Sana K | Yes | No | 9:30 | 18:00 | Settlement use case Doc understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case Doc preparation
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Executing Collateral Enter Cash scenarios for Deposit Type-Security Deposit in Nasdaq Validator 2. Discussed modified trade flow TC & explained CB10025 message to Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Preparing test cases for rectified trade flow(total 14 messages done);executing load combination for performance testing;discussed with mentees on open questions for PT
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Finished test cases for settlement orchestrator messages
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 29-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case Doc preparation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing use case Doc preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use Case query Dicussion
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use Case query Dicussion
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case ppt preparation
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case Doc preparation
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing use case Doc understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case ppt preparation
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Executing Collateral Enter Cash scenarios for Deposit Type-Security Deposit in Nasdaq Validator 2. Discussed modified trade flow TC & explained BD39 message to Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Preparing test cases for rectified trade flow(total 17 messages done);discussed test execution plan/open questions with nishant sir and mentees
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Tosca integration with git in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 30-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing use case Doc preparation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing use case Doc preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use Case query Dicussion
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use Case query Dicussion
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case ppt preparation
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case Doc preparation
7 | Sana K | Yes | No | 9:30 | 18:00 | Settlement use case Doc understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case ppt preparation
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Executing Collateral Withdraw Cash scenarios for Deposit Type- Security Deposit in Nasdaq Validator 2. Discussed the Modified Trade flow TC with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Preparing test cases for rectified trade flow(Done with total 18 messages and 1 scenario);executing load combination for performance testing
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Git and tosca integration with Jenkins complete
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 04-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing KT Preperation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoretical Pricing Presentation and Risk Queries Preperation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk Use Cases KT Preparation
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral Use cases KT preparation
7 | Sana K | Yes | No | 9:30 | 18:00 | KT for settlement and KT preparation for Clearing use cases
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk Use Cases KT Preparation
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed Collateral Withdraw Cash scenarios for Deposit Type- Security Deposit in Nasdaq Validator 2. Discussed the Modified Trade flow with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Discussed open questions with nishant sir and mentees for PT; Discussed the Modified trade flow with Pratiksha for FO and CM through validator ; Create sheet for FO with new broadcast messages(Additional)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Documentation : git and jenkins integration with tosca
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 05-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing Use Cases KT Prep
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Pricing DPD KT PPT preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Use Case Query Discussion
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Use Case Query Discussion
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | KT doc review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Query discussion of collateral use cases and rework of document
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing Use Cases KT Prep
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Internal KT prep for Risk use cases documents
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.note down queries regarding API collateral flow for deposit type- Security deposit 2. Discussed queries regarding Modified trade flow with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Done with message description sheet for FO (normal rectify scenario);Discussed queries with Pratiksha on rectify quantity scenario
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Selenium framework building
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 06-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing Use Cases KT Prep
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Pricing DPD KT PPT preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Use Case Query Discussion
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Use Case Query Discussion
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Internal KT prep for Risk use cases documents
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral Use cases rework of document
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing Use Cases KT Prep
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Internal KT prep for Risk use cases documents
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Note down queries regarding API Modified trade flow for 1.Rectify Quantity 2. Normal Rectify trades for CM segment
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Understanding flow for normal rectify trades for FO segment; Internally discussed queries regarding: 1. Modified trade flow 2. Settlement positions for CM segment
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Selenium framework building
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 07-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | KT completed for clearing use cases document and Working on KT feedback points
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Pricing DPD KT PPT preparation and Worked upon Theoretical Pricing Feedback
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use Case Query Discussion & Self Appraisal
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use Case Query Discussion & Self Appraisal
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review Point changes for Risk Use cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral Use cases Walkthrough Preparation
7 | Sana K | Yes | No | 9:30 | 18:00 | KT completed for clearing use cases document and Working on KT feedback points
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review Point changes for Risk Use cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Working on the queries which were discussed with Rajat for API collateral 2. Discussed normal Rectify trades for CM & FO segment with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Discussed flow for normal rectify trade for CM and FO segment with Pratiksha
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Selenium framework building
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 08-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Working on KT clearing feedback points
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Pricing DPD PPT Preparation and Presentation
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Cross functional trainning and Review
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Cross functional trainning and Review
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | KT doc review changes for risk use case
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on KT collateral feedback points
7 | Sana K | Yes | No | 9:30 | 18:00 | Working on KT clearing feedback points
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | KT doc review changes for risk use case
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Discussed Rectify Trade flow queries with Niranjan & API tesing Team
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Discussed queries regarding rectify quantity trade flow and normal rectify trade for CM and FO segment with Niranjan
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Selenium framework building; Working on selenium cucumber
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 11-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Review Point changes for Clearing and Settlement
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Review Point changes for Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Verifying cross functional review points
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Verifying cross functional review points
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review Point changes for Risk Use cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case doc - updating review points for presentation and checking configuration
7 | Sana K | Yes | No | 9:30 | 18:00 | Review Point changes for Clearing and Settlement
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review Point changes for Risk Use cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Pruthvi & I updated the Rectify Quantity Test Cases
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Completed test cases for rectify quantity and normal quantity(total 28 messages and 29 test cases) trade flow for FO
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Selenium framework building
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 12-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Clearing STT Use case document Understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Use cases Understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Settlement Client Direct Payout Use case document Understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Clearing STT Use case document Understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Preparing structure using selenium and cucumber for settlement functional module
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 13-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing use case - Bond future doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Document understanding for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
8 | Forum Rathod | Yes | No | 9:22 | 18:00 | Clearing STT use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:05 | 18:00 | Working on Infra related issue; Updated test cases for Normal rectify trade flow for FO(total 28 messages and 31 test cases); Verifying the rectify quantity trade flow for FO
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Understanding the settlement regression test cases
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 14-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing use case - Bond future doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Document understanding for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
8 | Forum Rathod | Yes | No | 9:22 | 18:00 | Clearing STT use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:05 | 18:00 | updated test cases for rectify quantity trade flow for FO; prepared document of issues for CM segment
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Java git and Jenkins integration Settlement regression test cases analysis
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 15-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing use case - Bond future doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Document understanding for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case doc understanding
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:05 | 18:00 | Completed test cases for rectify quantity trade flow for FO(total 33 messages & 35 test cases) Discussed with Pranit regarding next task Prepared Message description sheet for rectify two trades for FO
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Cucumber architecture for Settlement Module Documentation of c2n
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 18-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 5
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc walkthrough and query discussion
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing use case test scenario design: 17
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 15
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 20
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case doc walkthrough and query discussion
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Completed test cases for rectify two trades scenario for FO(total 49 messages and 56 test cases); Prepared message description sheets for all rectify scenarios for CM; Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Git java and Jenkins integration and prepared documents for the same; Cucumber feature files for settlement module ready
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 19-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 13
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 14
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 19
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 13
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 30
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 17
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Verifying the collateral flow in icoretrace
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Completed test cases for normal rectify scenario for CM(total 32 messages and 33 test cases); Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Setting up vm for selenium framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 20-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 25
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 21
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 21
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 12
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 40
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 27
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating API Collateral Test Cases for Security Deposit Deposit Cash
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Completed test cases for rectify quantity and rectify two trade scenarios for CM; Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | vm setup for selenium
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 21-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 27
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 17
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case document understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Use case document understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 11
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 13
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 50
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 20
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed test cases writing for Collateral deposit cash for Checked - Checked Scenario for both the deposit types
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Working on test execution plan for performance testing; Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Setup with selenium code ready on VM machine
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 22-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 30
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 14
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case query discussion and Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Settlement query discussion and Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 13
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 12
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 60
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 16
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed test cases writing for Collateral Deposit cash for both the deposit types. 2. Discuss the Rectify Trade releated queries with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Working on test execution plan for performance testing; Discuss the Rectify Trade releated queries with Pratiksha
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Working on email notifications on Jenkins
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 26-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 38
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 20
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Use case query discussion and Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Settlement query discussion and Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 35
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 14
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 100
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 12
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Continuing with the test cases writing for Collateral Withdraw cash for both the deposit types.
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Understanding SLA document
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Preparing cucumber script
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 27-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 22
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 21
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding and query dicussion with Archana
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 40
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 16
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 84
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 12
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Continuing with the test cases writing for Collateral Withdraw cash for both the deposit types.
11 | Pruthviraj Jadhav | Yes | No | 9:20 | 18:00 | Working on Infra related issue
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | cucumber scripting for settlement module
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 28-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 15
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 12
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 35
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 15
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 59
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Test scenario design: 10 Modified Test cases : 27
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. Continuing with the test cases writing for Collateral Withdraw cash for both the deposit types. 2. Discussed with Rajat regarding OB10003 message
11 | Pruthviraj Jadhav | Yes | No | 9:15 | 18:00 | Working on Infra related issue; Working on load combinations for test execution plan for performance testing
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | cucumber scripting for settlement module
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 29-May
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 25
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 8 Modified Test cases : 13
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future use case test scenario design: 23
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 12
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 50
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case Modified Test cases : 9
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Preparing Rectify trade flow understanding document with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:15 | 18:00 | Working on understanding document preparation(Comparing Rectify quantity scenario for FO and CM)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Cucumber scripting for settlement module complete Step defination for the same remain Tosca installation pending on vm Lastest code for automation copy pasted on the vm Machine
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 01-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 25
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Working on Pricing use case revised document
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test case design for settlement client direct payout use case: 10
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 20
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Clearing STT use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Preparing Rectify trade flow understanding document with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:15 | 18:00 | Working on understanding document preparation(Comparing Rectify quantity scenario for FO and CM)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Step definition scripting Excel utility code in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 02-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral eds use case Test Scenario Design 15 and review
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Overall estimation Betawise & Review of Settlement Use case
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Overall estimation Betawise
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Working on Pricing use case revised document
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 30
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral EDS use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Preparing Rectify trade flow understanding document with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:15 | 18:00 | Working on understanding document preparation (Normal rectify scenario for FO and CM completed and working on Two trades flow)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Step Defination for cucumber complete Coding for reporting module Task list pending
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 03-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral eds use case Test Scenario Design 15 and review
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Overall estimation Betawise & Review of Settlement Use case
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Overall estimation Betawise
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Working on Pricing use case revised document
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario design: 25
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral EDS use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed Rectify trade flow understanding document with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:05 | 18:00 | Completed Rectify trade flow understanding document; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Report scripting in progress RDM cases with ng placed on vm machine
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 04-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS Test Scenario review
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case doc understanding
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Overall estimation Betawise & Review of Settlement Use case
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding & Overall estimation Betawise
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Working on Pricing use case revised document
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS Test Scenario preparation - 15 Test scenarios and review
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral EDS use case doc understanding + suggested Sana to add 6 negative scenarios
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Started Bash Scripting & Shell Programming (Linux Command Line) Understanding Clearing DPD document
11 | Pruthviraj Jadhav | Yes | No | 9:05 | 18:00 | Understanding Clearing DPD document for Rectified trade flow; Working on FIXML utility with Postman; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Discussion with functional team for rdm test cases Rdm test case suite to cucumber scripting in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 05-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral Hairut test case review changes
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 26
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Review of Settlement Use case and Interop BR
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral Haircut use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1. As discussed with Nitesh, Verifying the Response message description for Collateral Enter Security & comparing the flow and fields with Collateral Cash scenarios & finding difference if any. 2. Continuing Bash Scripting & Shell Programming (Linux Command Line) training
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding Clearing DPD document for Rectified trade flow; Working on FIXML utility with Postman; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Account demo code ready; Reading rdm test cases; Raised query for vm machine
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 08-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral Hairut test case review changes
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 23
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Review of Settlement Use case and Interop BR
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral Haircut use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Preparing Deposit security test cases for margin & security deposit
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Working on FIXML utility with Postman; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Going to rdm test cases account module; Started course for devops : jenkins , gradle and maven; Had discussion with Sudhir shukla for the framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 09-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral Hairut test case review changes
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 29
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Review of Collateral Use case and Interop BR
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding and Review of pricing Use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement client direct payout use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral Haircut use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | A. Completed test cases writing for deposit security: 1.Apply Collateral Check: Checked Send Swift- Checked 2.Apply Collateral Check: Unchecked Send Swift- Checked For both the deposit types B. Started 2nd e-learning course- Building UI automation test framework with selenium framework
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Executing Normal trade flow test cases; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Reading rdm test cases; Making poc for parameterized xpath framework; E-learning course for Jenkins maven and gradle
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 10-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral Hairut test case review changes
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 47
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Review of Collateral Use case and Interop BR
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding and Review of pricing Use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement number
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review and test scenario design - 15
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral Haircut use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | A. Completed test cases writing for deposit security: 1.Apply Collateral Check: Unchecked Send Swift- Unchecked 2.Apply Collateral Check: Checked Send Swift- Unhecked For both the deposit types. B. Started with Withdraw Security Scenarios
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Completed series creation script with postman; Executing Normal trade flow test cases; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Reading rdm test cases; Poc development; E-learning courses
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 11-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral Hairut test case review changes
2 | Mohammed Shadab | Yes | No | 9:50 | 18:00 | Clearing STT use case Test scenario design: 25
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Working on estimation sheet and Use case review
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Working on estimation sheet and Use case review
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Pricing Bond Future Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Working on review points for settlement number
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review and test scenario design - 20
8 | Forum Rathod | Yes | No | 9:35 | 18:00 | Collateral Haircut use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | A. Completed test cases writing for withdraw security: 1.Apply Collateral Check: Checked Send Swift- Checked 2.Apply Collateral Check: Unchecked Send Swift- Checked For both the deposit types
11 | Pruthviraj Jadhav | Yes | No | 9:20 | 18:00 | Executing Normal trade flow test cases; Going through e-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Xpath poc parameterization complete; Rdm test cases for modification scripting in progress; E-learning for jenkins
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 12-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS test case review changes
2 | Mohammed Shadab | Yes | No | 9:40 | 18:00 | Walkthrough of clearing stt use cases and Test scenario design: 10
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Reverse KT with Shadab and review discussion for Settlement review point
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Reverse KT with Shadab and Interop
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Settlement Number test case Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Settlement Use case witheld Review changes
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review and test scenario design - 15
8 | Forum Rathod | Yes | No | 9:22 | 18:00 | Clearing STT use case new doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed test case writing for Deposit & Withdraw Security Scenarios
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Executing Normal trade flow test cases; Going through E-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Prioritising rdm modification test cases; E-learning Jenkins course
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 15-Jun
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review changes
2 | Mohammed Shadab | Yes | No | 9:40 | 18:00 | clearing stt use casesTest scenario design: 21
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Discussion on settlement review points and Interop BR
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Interop BR Document Understanding
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Settlement Use case withheld Review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Settlement Use case withheld Review changes
7 | Sana K | Yes | No | 9:30 | 18:00 | Collateral EDS use case Test scenario review
8 | Forum Rathod | Yes | No | 9:38 | 18:00 | Document Understanding, Test scenarios: Modified - 6, New - 2
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Discussed with Deepti regarding SO Configuration Had a call with Laxmi regarding OB10003 issue for Enter Security Understand SO API flow with Gautami
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 18:00 | Executing Normal trade flow test cases; Going through E-learning courses
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Scripting for Accounts module Jenkins course completion KT to Pratiksha on Settlement API
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM