## 19-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | No | Yes | 8.45 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10.15 | 6.2 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | No | Yes | 9.45 | 5.45 | Understanding Use Cases_Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Understanding Document of Interoptebilty and Interim review of theoretical prices
5 | Kritika Manek | Yes | No | 9.5 | 5.45 | Test Scenario and Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9.5 | 5.3 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request for CM Segment
9 | Nitesh Bedi | Yes | No | 9:50 | 6:30 | Understanding the "Settlement Module FD" for meeting scheduled for tomorrow; Working on scenarios for Performance Testing
10 | Pratiksha Talekar | Yes | No | 9:30 | 6 | Test case preparation forAPI Testing - Collateral flow; discussed "Modified Trade" flow with Nitesh
11 | Pruthviraj Jadhav | Leave | No | NA | NA
12 | Gautami Karkal | Leave | No | NA | NA

## 20-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 11 | 4 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | No | Yes | 10 | 4 | Theoretical Prices - Made changes in Test Cases as per review points
3 | Mohnish Motwani | Yes | No | 9.45 | 5.45 | Mentoring of team, Settlement Webex Session and Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 10 | 6 | Settlement Webex Session, Team Discussion and Understanding Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Scenario and Test Cases writing for Clearing DPD and Settlement Webex Session
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Gsec Deposit for CD and Debt
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Funds EPI - EPI Request and Allocation for CM Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 5:30 | Reviewing performance testing scenarios; Understanding settlement flow
10 | Pratiksha Talekar | Yes | No | 9:30 | 5:30 | Test case preparation forAPI Testing - Collateral flow completed; Review pending with Nitesh
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 5:30 | Prepared test scenarios for performance testing; setting up automation tools
12 | Gautami Karkal | Yes | No | 10:15 | 5:15 | Started with CI/CD tools integration with TOSCA and Selenium

## 23-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9.3 | 5.45 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9.45 | 6 | Test Cases on Theoretical Pricing and restructuring of formula
3 | Mohnish Motwani | Yes | No | 9.45 | 6 | Understanding use case of settlement and Physical Settlement document
4 | Amardas Gangula | Yes | No | 9.45 | 6 | TC Review of Therotical Pricing and document understanding of Physical Settlement
5 | Kritika Manek | Yes | No | 9.3 | 6 | Test Cases writing for Clearing DPD Theoretical price review
6 | Kabir Gor | Yes | No | 9.3 | 5.45 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI
8 | Forum Rathod | Yes | No | 9.3 | 6 | Test Cases writing for CIM - Fund EPI Allocation, Securties EPI (CM &SLB)
9 | Nitesh Bedi | Yes | No | 9:30 | 6:30 | Discussion on performance testing scenarios; Understanding settlement flow; Reviewing "API Collateral Test cases"
10 | Pratiksha Talekar | Yes | No | 9:30 | 6:00 | Test case preparation forAPI Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 10:00 | 6:30 | Prepared test scenarios for performance testing; Initiated discussion with Ami/Laxman; set up automation tools
12 | Gautami Karkal | Yes | No | 10:00 | 5:45 | Created new project with Selenium; Set up Jenkins

## 24-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test case preparation for Pricing DPD and Clearing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Team Discussion, Understanding Physical Settlement and review of Pricing Test cases
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario and Test Cases writing for Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposits for CM segments
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Reviewing "API Collateral Test cases"; scheduled meeting with mentee's on performance testing approach; set up of git and ci/cd in progress
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Initiated discussion and prepared questionaire for discussion with mentees; set up automation tools; started with automation script
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | setup of jenkins and selenium project; command line execution of executable using Jenkins
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 25-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test cases preparation of Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement.
4 | Amardas Gangula | Yes | No | 9:30 | 18:00 | Team Discussion, Understanding Physical Settlement document, Webex session on settlement,TC Review of Therotical Pricing
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases writing for Clearing DPD
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Fund EPI - Request and Allocation
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Deposit for FO segment
9 | Nitesh Bedi | Yes | No | 9:00 | 17:30 | Review and discuss "API Collateral Test cases"; Discusssion on PT - open questions
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Discussion with mentees on PT open questions; set up automation tools - selenium and GIT
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Jenkins plugins for selenium;Login script for orange hrms ready
13 | Anita Shinde | Yes | No | 10:00 | 18:00 | PM

## 26-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Cases on Pricing DPD and Theoretical Pricing Review
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Reviewed point discussed of Theoretical Pricing, Understanding Physical Settlement Document
5 | Kritika Manek | Yes | No | 9:00 | 17:30 | Test Cases on Clearing DPD and Theoretical Pricing Review
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Going through SLA Document for PT; setup of Git; Review of API Collateral test cases
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Checked scenario) and (Deposit Cash - Checked /Unchecked scenario)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document;set up automation tools - selenium; Sample script created
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | Login script for orange hrms ready; automated execution using Jenkins in progress
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 27-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:10 | Test Cases on Pricing DPD, Discussion and Review of Throretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion, Resolving queries of Collateral Use case, Understanding use case of Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Reviewed point discussed of Theoretical Pricing and reviewed test cases of Clearing DPD
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Creation of Document for JIRA
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Cases writing for Settlement Orchestrator FD & Settlement Technical Session
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release File Upload
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Securities Release Request
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Review of API Collateral test cases; Understanding SLA document for PT; Going through settlement FD
10 | Pratiksha Talekar | Yes | No | 9:00 | 17:30 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Checked /Unchecked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:30 | Understanding SLA document; Shared questions to be discussed on Monday with Mentees
12 | Gautami Karkal | Yes | No | 10:00 | 17:00 | automated execution using Jenkins-currently facing issues; Understanding the Settlement Orchestrator FD
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 30-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 10:00 | 18:00 | Test cases on Pricing DPD and Theoretical Pricing
3 | Mohnish Motwani | Yes | No | 9:45 | 18:45 | Reviewed point of SO FD discussed with team and discussed/resolved queries of Use case collateral.
4 | Amardas Gangula | Yes | No | 9:45 | 18:45 | Reviewed point of Theoretical Pricing discussed with team and queries discussed with Mentees.
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Test Cases in Clearing Use Cases and Theoretical Pricing
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases on Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release CM Segment
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Release CD Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /Unchecked scenario)-Settled
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 31-Mar
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test scenarios and Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test cases on Pricing DPD
3 | Mohnish Motwani | Yes | No | 9:45 | 19:00 | Review meeting(Client & Team),reviewed point of SO FD discussed with team and discussed/resolved queries of Use case collateral.
4 | Amardas Gangula | Yes | No | 9:45 | 19:00 | Review meeting(Client & Team),Reviewed point of Theoretical Pricing, Clearing DPD discussed with team and queries discussed with Mentees.
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Document Understanding of Clearing Use Cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases on Settlement Orchestrator FD
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release FO Segment
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Cases writing for CIM - Gsec Release for Debt Segment
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Setup of Git; Understanding SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Updating test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /checked scenario)-Manually Settled and Manually Rejected
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 10:00 | 18:00 | Understanding the Settlement Orchestrator FD; Git setup
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 01-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Case writing for Collateral Haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Understanding of Risk Use Cases
3 | Mohnish Motwani | Yes | No | 9:45 | 18:00 | Use case document understanding Settlement and query resolving Collateral
4 | Amardas Gangula | Yes | No | 9:45 | 18:00 | Use case document understanding Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Understanding of Clearing Use Cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Understanding of Settlement Use Cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Review of Collateral Haircut Test Cases
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Understanding of Clearing Use Cases
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Discussion on Git setup with the team; Discussion on SLA document for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Created test cases for API Testing - Collateral flow (Deposit Cash - Unchecked /checked and Unchecked/Unchecked - Settled; All scenarios for Deposit Cash:Margin Deposit completed
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document;Git setup; Cucumber set up
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Setup Of Git Bash and Git GUI ; Understanding Basic Git Commands ;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 03-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Haircut use cases review changes
2 | Mohammed Shadab | Yes | No | - | - | Leave
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Use case document understanding Settlement and query resolving Collateral with Deba
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Use case document understanding Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 17:45 | Clearing use case Test scenario design
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Document Understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Haircut use cases test case design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Clearing use case Test scenario design
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Understanding the SLA document; Planned discussion on the Settlement module
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Understanding Modified trade flow For following scenarios1.Trade Insert - for Cash Market2. Rectify Quantity
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding the SLA document; Setup of Cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 17:30 | Git Basic Understanding Complete ;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 07-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Understanding of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:15 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:15 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 17:30 | Going through the Interface Flow diagram; preparing points for meeting with mentees on PT SLA
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted-> Settled)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding SLA document and Interface service flow; working on cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Working on keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 08-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario review changes for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Scenario Creation of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Discussion on SLA document for PT with Mentees; Going through the Interface Flow diagram; Scheduled meetings to discuss on the Modified Trade and Settlement flow
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted->Manually Settled); Understanding Modified Trade Flow for Rectify Quantiy
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Discussion on SLA document for PT; Working on cucumber
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Working on keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 09-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Test Scenario review changes for Collateral haircut
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Test Scenario Creation of Risk Mark to Market Cash Segment FD
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement session with non functional team
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Settlement Withheld of securities
7 | Sana K | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Collateral haircut
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Test Scenario Creation for Clearing offline position
9 | Nitesh Bedi | Yes | No | 9:30 | 18:00 | Started with Test Execution plan for PT; Discussed review comments with Pruthvi on Trade flow test cases; Had internal team call for functional walk through of settlement module; Completed reverse KT/open questions with Niranjan on the Modified Trade Flow
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-Checked-Margin Deposit Scenario(for Created->Accepted->Manually Rejected)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Preparing ppt for PT ; Discussion on normal trade flow test cases; Discussion on rectified trade flow with nirajan; Dicussion on settlement module
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Completed with Keyword driven framework
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 13-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use case test scenario design
3 | Mohnish Motwani | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Collateral and Settlement
4 | Amardas Gangula | Yes | No | 9:45 | 18:30 | Team Discussion and Use case document understanding for Clearing and Risk
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review of Test scenario for clearing use cases
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Test cases design for settlement use case
7 | Sana K | Yes | No | 9:30 | 18:00 | Test cases design for collateral use case
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review of Test scenario for clearing use cases
9 | Nitesh Bedi | Yes | No | 9:30 | 18:30 | Preparing PT Execution Plan; Reviewing trade flow test cases; Setting up Jenkins and Selenium
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-Checked-Margin Deposit Scenario(for Created->Accepted->Settled) Explained Modified Trade flow to Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding Modified Trade flow; Preparation of test cases for modified trade flow
12 | Gautami Karkal | Yes | No | 9:00 | 18:00 | Read FD for Settlement Orchestrator and prepared Flow for the same;
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 15-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use case documnet understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | PPT preparation of risk doc
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of settlement Withheld security
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of Clearing Offline Position Limit
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Review changes incorporation of Settlement use case doc
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use case documnet understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
9 | Nitesh Bedi | Yes | No | 9:30 | 18:30 | Preparation of the PT Test execution ppt; Understanding the Interface flow diagram
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-Checked-Margin Deposit Scenario(for 1. Created->Accepted->Manually Settled 2. Created->Accepted->Manually Rejected) Reviewed Normal Trade flow Test cases which is written by Pruthvi & after reviewing updated those test cases based on the flow.
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | Understanding Modified Trade flow; Prepared test scenarios for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Upload Java Code in git
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 16-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use cases test scenario designed
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases test scenario designed
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of Collateral Haircut
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of M2M
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SO CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use cases test scenario designed
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Review changes incorporation of Clearing use case doc
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Working on "Test execution plan" for PT; reviewing trade flow test cases; Checking on application connection issues through VDI
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | Completed with Test Cases Writing for Collateral Withdraw Cash - UnChecked-UnChecked-Margin Deposit Scenario(for Created->Accepted-> Settled
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 18:00 | setup for VDI ;Preparation of test cases for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Test flow diagram for SO and understanding SO message code
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 17-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Risk use cases test scenario design
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases test scenario design
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Use case review of Collateral Haircut
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Use case review of M2M
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Theoritical pricing test case review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SO CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use cases test scenario design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Mapping of mindtree clearing test cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Preparing PT "Test execution" plan; reviewed SO flow scenarios; Checking on application access issue from remote desktop
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Withdraw Cash - Checked-UnChecked-Margin Deposit Scenario(for Created->Accepted-> Settled) 2. Disussed the queries regarding CB0 message with Pruthvi
11 | Pruthviraj Jadhav | Yes | No | 9:10 | 17:55 | Understanding CB0 fields validation on validator;Preparation of test cases for normal trade flow
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Prepared test scenarios for SO
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 20-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing Use cases (Offline Position Limit) document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Review of Theoretical Prices Test Cases
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Theoritical pricing test case review changes
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SSI CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing Use cases (Offline Position Limit) document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Mapping of mindtree clearing test cases
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | Working on PPT and "Test execution plan" for PT
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - Checked-Checked- Security Deposit Scenario (for a. Created->Accepted-> Settled b. Created->Accepted-> Manually Settled) 2. Discussed with Pruthvi on what Testcases should be included to cover CD284 broadcast message
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Prepared test cases for normal trade flow; Preparing test cases for rectified trade flow(1st 3 broadcast messages completed)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Tosca Installation and Setup ; Started with the orange hrms automation
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 21-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Theoritical pricing walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Cross functinal trainning
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Worked on Review changes made by Archana Ma'am for SSI CD cases
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - Checked-Checked- Security Deposit Scenario (for a. Created->Accepted-> Manually Rejected) Collateral Deposit Cash - Unchecked-Checked- Security Deposit Scenario (for a. Created->Accepted->Settled)
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Preparing test cases for rectified trade flow(5 broadcast messages completed)
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Tosca cl client setup ready;Tosca with jenkins integration completed;result printing on jenkins pending;review from nitesh pending
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 22-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Settlement use case document understanding
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Review of Settlement Orchestartor/SSI cases review points
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Cross functional trainning
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Clearing use case document understanding
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Completed with Test Cases Writing for Collateral Deposit Cash - UnChecked-Checked- Security Deposit Scenario 2. Discussed with Pruthvi on modified trade flow tc
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:45 | Preparing test cases for rectified trade flow(6 broadcast messages completed);Discussed with pratiksha on one broadcast message
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Completed tosca result printing on jenkins; Rectified test flow and scenario after review from nitesh
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM

## 23-Apr
Sr.No | Employee Name | Work From Home status | Worked From NSE | Log-In Time | Log-Out Time | One-liner on work done
1 | Roshni Kumar | Yes | No | 9:30 | 18:00 | Clearing use case document summary preparation
2 | Mohammed Shadab | Yes | No | 9:45 | 18:00 | Risk use cases walkthrough preparation
3 | Mohnish Motwani | Yes | No | 9:45 | 19:30 | Cross functional trainning
4 | Amardas Gangula | Yes | No | 9:45 | 19:30 | Incorporation of review points of Risk use case
5 | Kritika Manek | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
6 | Kabir Gor | Yes | No | 9:30 | 18:00 | Collateral use case document understanding
7 | Sana K | Yes | No | 9:30 | 18:00 | Risk use case doc review test scenario design
8 | Forum Rathod | Yes | No | 9:30 | 18:00 | Risk use case doc understanding
9 | Nitesh Bedi | Yes | No | 9:45 | 18:30 | -
10 | Pratiksha Talekar | Yes | No | 9:00 | 18:00 | 1.Discussed Modified Trade Flow Test Cases with Pruthvi 2. Checked Security Deposit flow for Checked - Checked scenario in validator
11 | Pruthviraj Jadhav | Yes | No | 9:00 | 17:55 | Updated test cases for rectified trade flow; Preparing test cases for rectified trade flow(7 broadcast messages completed);Discussed with pratiksha on one broadcast message
12 | Gautami Karkal | Yes | No | 9:15 | 18:00 | Writing test cases for settlement orchestrator
13 | Anita Shinde | Yes | No | 10:00 | 18:30 | PM